## Sheet1
Project name | Project context | Priority | Roles | Workers per role | Role hours per week | Mandatory | Deadline | Estimated duration (weeks) | Depends on | Conflicts with
Network Core Switch Replacement | Replace aging campus core switches, update routing and VLAN configurations, coordinate maintenance windows, and validate redundancy and failover. | 3 | Project Manager, Network Specialist, Systems Administrator, Tester | Network Specialist: 2 | Network Specialist: 8, Systems Administrator: 5 | Yes | 2026-09-18 | 5
Campus Wi-Fi Expansion | Expand wireless coverage in classrooms, residences, and outdoor student spaces using new access points, site surveys, controller configuration, and performance testing. | 3 | Project Manager, Network Specialist, Systems Administrator, Tester | Network Specialist: 2 | Network Specialist: 8, Tester: 5 | Yes | 2026-11-06 | 6 | Network Core Switch Replacement | Classroom AV Modernization
MFA Expansion for Privileged Systems | Extend multi-factor authentication to administrative consoles, privileged accounts, VPN access, and critical infrastructure while documenting exception and recovery procedures. | 3 | Project Manager, Security Analyst, Systems Administrator, Tester |  | Security Analyst: 7, Systems Administrator: 5 | Yes | 2026-09-11 | 4
Student Portal Accessibility Upgrade | Remediate accessibility issues in the student portal, improve keyboard navigation and screen-reader compatibility, update forms, and complete WCAG-focused usability testing. | 3 | Project Manager, Business Analyst, Programmer, Tester | Tester: 2 | Programmer: 7, Tester: 6 | Yes | 2026-10-02 | 5
Research Data Storage Migration | Migrate faculty research data from legacy storage to a resilient managed platform with access controls, backup validation, data transfer planning, and researcher communication. | 2 | Project Manager, Systems Administrator, Database Administrator, Security Analyst |  | Systems Administrator: 7, Database Administrator: 6 | No | 2026-11-20 | 6 | Network Core Switch Replacement
Classroom AV Modernization | Upgrade audiovisual technology in selected teaching spaces, including displays, control systems, lecture capture, cabling, installation coordination, and faculty acceptance testing. | 2 | Project Manager, Systems Administrator, Support Specialist, Tester | Support Specialist: 2 | Support Specialist: 7, Systems Administrator: 5 | No | 2026-12-04 | 7 |  | Campus Wi-Fi Expansion
IT Knowledge Base Refresh | Review and rewrite high-use IT support documentation for students, faculty, and staff, retire obsolete articles, standardize screenshots, and improve search keywords and ownership. | 2 | Project Manager, Technical Writer, Support Specialist, Business Analyst | Technical Writer: 2 | Technical Writer: 6 | No | 2026-09-25 | 3
Service Desk AI Chatbot Pilot | Pilot an AI-assisted service desk chatbot using approved knowledge articles, privacy controls, escalation rules, response evaluation, and a limited student-facing deployment. | 1 | Project Manager, Programmer, Support Specialist, Security Analyst, Tester |  | Programmer: 6, Support Specialist: 5, Tester: 5 | No | 2026-10-30 | 4 | IT Knowledge Base Refresh
Disaster Recovery Tabletop and Failover Test | Conduct a university IT disaster recovery exercise covering major systems, communication procedures, backup restoration, failover testing, recovery objectives, and lessons learned. | 3 | Project Manager, Systems Administrator, Security Analyst, Business Analyst, Tester |  | Systems Administrator: 6, Tester: 5 | Yes | 2026-11-27 | 3 | Research Data Storage Migration
IT Asset Management System Implementation | Implement a centralized asset management system for laptops, desktops, peripherals, warranties, assignments, lifecycle status, and reporting, including data cleanup and staff training. | 2 | Project Manager, Business Analyst, Programmer, Systems Administrator, Trainer |  | Programmer: 6, Business Analyst: 5 | No | 2026-12-18 | 6

## Instructions
Column | How to use it
Project name | Required. Enter one project per row.
Project context | Optional. Briefly describe the project’s purpose, topic, deliverables, technologies, audience, and special requirements. This text is used during Q-matrix generation to compare the project context against each worker’s skills and profile. Include specific keywords that should influence worker suitability, such as AI policy, networking, accessibility, documentation, security, student support, or data analysis. Avoid vague descriptions such as complete project work.
Priority | Required. Use 1, 2, or 3 where 3 is highest priority.
Roles | Required. Comma-separated roles, for example: Project Manager, Programmer, Tester.
Workers per role | Optional. Only enter values when a role needs more than the default. Blank uses the app default of 1 worker per selected role. Example: Programmer: 2.
Role hours per week | Optional. Only enter values when a role uses a non-default number of hours. Blank uses the app default of 4 hours/week per selected role.
Mandatory | Optional. Use Yes/No or TRUE/FALSE.
Deadline | Optional. Use a date.
Estimated duration (weeks) | Optional. Blank or missing values default to 1 week in the app.
Depends on | Optional. Comma-separated existing project names that must finish first.
Conflicts with | Optional. Comma-separated existing project names that cannot run at the same time.